## App_II_consolidated
ACGT_Appendix_II_ Budget vs. Actual Costs
Cost Budget Follow-up Table
Contract N: 026996 |  | Acronym: ACGT
Integrated Appendix |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
01 TO 26 | in P/M | Total Person-month | 1811 | 482.53 | 79.23 | 561.76 | 26.64% | 1328.47
|  | Direct Costs | 11470678 | 2358716.1586 | 487421.59 | 2846137.7486 | 20.56% | 9111961.8414
| € | Personnel costs | 9720784.56 | 1902831.09 | 349254.51 | 2252085.6 | 19.57% | 7817953.47
| € | Subcontract costs (except audit) | 172000 | 2586.2 | 0 | 2586.2 | 1.504% | 169413.8
| € | Subcontract (audit costs only) | 87000 | 0 | 0 | 0 | 0% | 87000
| € | Travel costs | 921338.27 | 263442.12 | 28660 | 292102.12 | 28.59% | 657896.15
| € | Other costs and equipement | 569555.17 | 189856.7486 | 7412 | 197268.7486 | 33.33% | 379698.4214
| € | Indirect costs | 5276528 | 1127524.1557 | 42690.28 | 1170214.4357 | 21.37% | 4149003.8443
|  | Total costs | 16747206 | 3486240.3143 | 530111.87 | 4016352.1843 | 20.82% | 13260965.6857

## ERCIM_appII_all partners
ERCIM |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
1 | in P/M | Total Person-month | 65 | 12.7 |  | 12.7 | 19.54% | 52.3
|  | Direct Costs | 456243 | 111013.05 | 0 | 111013.05 | 24.33% | 345229.95
| € | Personnel costs | 279243 | 78545.97 |  | 78545.97 | 28.13% | 200697.03
| € | Subcontract costs (except audit) | 0 |  |  | 0 | #DIV/0! | 0
| € | Subcontract (audit costs only) | 87000 |  |  | 0 | 0% | 87000
| € | Travel costs | 50000 | 12826.07 |  | 12826.07 | 25.65% | 37173.93
| € | Other costs and equipement | 40000 | 19641.01 |  | 19641.01 | 49.1% | 20358.99
| € | Indirect costs | 357557 | 72018.57 |  | 72018.57 | 20.14% | 285538.43
|  | Total costs | 813800 | 183031.62 | 0 | 183031.62 | 22.49% | 630768.38
FORTH |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
2 | in P/M | Total Person-month | 154 | 68.35 |  | 68.35 | 44.38% | 85.65
|  | Direct Costs | 879873 | 276494.53 | 0 | 276494.53 | 31.42% | 603378.47
| € | Personnel costs | 609873 | 206333.85 |  |  | 33.83% | 403539.15
| € | Subcontract costs (except audit) | 50000 |  |  |  | 0% | 50000
| € | Subcontract (audit costs only) |  |  |  |  | #DIV/0! | 0
| € | Travel costs | 210000 | 68582.14 |  |  | 32.66% | 141417.86
| € | Other costs and equipement | 10000 | 1578.54 |  |  | 15.79% | 8421.46
| € | Indirect costs | 995846 | 239347.27 |  |  | 24.03% | 756498.73
|  | Total costs | 1875719 | 515841.8 | 0 | 276494.53 | 27.5% | 1359877.2
INRIA |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
3 | in P/M | Total Person-month | 66 | 18.66 |  | 18.66 | 28.27% | 47.34
|  | Direct Costs | 403392 | 113927.48 | 0 | 113927.48 | 28.24% | 289464.52
| € | Personnel costs | 363392 | 98101.61 |  |  | 27% | 265290.39
| € | Subcontract costs (except audit) |  |  |  |  | #DIV/0! | 0
| € | Subcontract (audit costs only) |  |  |  |  | #DIV/0! | 0
| € | Travel costs | 40000 | 15825.87 |  |  | 39.56% | 24174.13
| € | Other costs and equipement |  |  |  |  | #DIV/0! | 0
| € | Indirect costs | 282018 | 65809.79 |  |  | 23.34% | 216208.21
|  | Total costs | 685410 | 179737.27 | 0 | 113927.48 | 26.22% | 505672.73
UvA |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
4 | in P/M | Total Person-month | 53 | 14.6 | 5 | 19.6 | 27.55% | 38.4
|  | Direct Costs | 431802 | 71157.93 | 49320 | 120477.93 | 16.48% | 360644.07
| € | Personnel costs | 397533 | 51649.72 | 49320 |  | 12.99% | 345883.28
| € | Subcontract costs (except audit) |  |  |  |  | #DIV/0! | 0
| € | Subcontract (audit costs only) |  |  |  |  | #DIV/0! | 0
| € | Travel costs | 23852 | 7976.89 |  |  | 33.44% | 15875.11
| € | Other costs and equipement | 10417 | 11531.32 |  |  | 110.7% | -1114.32
| € | Indirect costs | 86361 | 14231.58 |  |  | 16.48% | 72129.42
|  | Total costs | 518163 | 85389.51 | 49320 | 120477.93 | 16.48% | 432773.49
Philips |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
5 | in P/M | Total Person-month | 115 | 34.9 |  | 34.9 | 30.35% | 80.1
|  | Direct Costs | 939522 | 177830 | 0 | 177830 | 18.93% | 761692
| € | Personnel costs | 939522 | 177830 |  | 177830 | 18.93% | 761692
| € | Subcontract costs (except audit) |  |  |  | 0 | #DIV/0! | 0
| € | Subcontract (audit costs only) |  |  |  | 0 | #DIV/0! | 0
| € | Travel costs |  |  |  | 0 | #DIV/0! | 0
| € | Other costs and equipement |  |  |  | 0 | #DIV/0! | 0
| € | Indirect costs | 896787 | 164987 |  | 164987 | 18.4% | 731800
|  | Total costs | 1836309 | 342817 | 0 | 342817 | 18.67% | 1493492
IJB |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
6 | in P/M | Total Person-month | 62 | 8.3 | 8.97 | 17.27 | 13.39% | 53.7
|  | Direct Costs | 450680 | 121567.45 | 52379 | 173946.45 | 26.97% | 329112.55
| € | Personnel costs | 305000 | 49804 | 52379 | 102183 | 16.33% | 255196
| € | Subcontract costs (except audit) |  |  |  | 0 | #DIV/0! | 0
| € | Subcontract (audit costs only) |  |  |  | 0 | #DIV/0! | 0
| € | Travel costs | 27216 | 4400.45 |  | 4400.45 | 16.17% | 22815.55
| € | Other costs and equipement | 118464 | 67363 |  | 67363 | 56.86% | 51101
| € | Indirect costs | 90136 | 24313.49 |  | 24313.49 | 26.97% | 65822.51
|  | Total costs | 540816 | 145880.94 | 52379 | 198259.94 | 26.97% | 394935.06
SIB |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
7 | in P/M | Total Person-month | 62 | 15 | 1.3 | 16.3 | 24.19% | 47
|  | Direct Costs | 372851 | 91869.75 | 9644.51 | 101514.26 | 24.64% | 280981.25
| € | Personnel costs | 347706 | 83631.2 |  |  | 24.05% | 264074.8
| € | Subcontract costs (except audit) |  |  |  |  | #DIV/0! | 0
| € | Subcontract (audit costs only) |  |  |  |  | #DIV/0! | 0
| € | Travel costs | 21105 | 8238.55 |  |  | 39.04% | 12866.45
| € | Other costs and equipement | 4040 |  |  |  | 0% | 4040
| € | Indirect costs | 74570 | 18373.95 |  |  | 24.64% | 56196.05
|  | Total costs | 447421 | 110243.7 | 9644.51 | 101514.26 | 24.64% | 337177.3
LundU |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
8 | in P/M | Total Person-month | 84 | 19.41 | 1.25 | 20.66 | 23.11% | 64.59
|  | Direct Costs | 398899 | 63005.64 | 17020 | 80025.64 | 15.79% | 335893.36
| € | Personnel costs | 376320 | 57509.04 | 9608 |  | 15.28% | 318810.96
| € | Subcontract costs (except audit) |  | 0 | 0 |  | #DIV/0! | 0
| € | Subcontract (audit costs only) |  | 0 | 0 |  | #DIV/0! | 0
| € | Travel costs | 22579 | 5442.11 | 0 |  | 24.1% | 17136.89
| € | Other costs and equipement |  | 54.49 | 7412 |  | #DIV/0! | -54.49
| € | Indirect costs | 79780 | 12601.13 | 0 |  | 15.79% | 67178.87
|  | Total costs | 478679 | 75606.77 | 17020 | 80025.64 | 15.79% | 403072.23
UMA |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
9 | in P/M | Total Person-month | 71 | 15.5 | 5 | 20.5 | 21.83% | 55.5
|  | Direct Costs | 326149 | 59310.8986 | 8062.56 | 67373.4586 | 18.19% | 266838.1014
| € | Personnel costs | 240149 | 36989.75 |  |  | 15.4% | 203159.25
| € | Subcontract costs (except audit) | 50000 | 2586.2 |  |  | 5.172% | 47413.8
| € | Subcontract (audit costs only) | 0 | 0 | 0 |  | #DIV/0! | 0
| € | Travel costs | 24000 | 13959.85 |  |  | 58.17% | 10040.15
| € | Other costs and equipement | 12000 | 5775.0986 |  |  | 48.13% | 6224.9014
| € | Indirect costs | 65230 | 11344.9397 |  |  | 17.39% | 53885.0603
|  | Total costs | 391379 | 70655.8383 | 8062.56 | 67373.4586 | 18.05% | 320723.1617
UPM |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
10 | in P/M | Total Person-month | 140 | 51.98 |  | 51.98 | 37.13% | 88.02
|  | Direct Costs | 703378 | 241846.06 | 0 | 241846.06 | 34.38% | 478155.99
| € | Personnel costs | 636708.73 | 225222.01 |  | 225222.01 | 35.37% | 411486.72
| € | Subcontract costs (except audit) |  |  |  |  | #DIV/0! | 0
| € | Subcontract (audit costs only) |  |  |  |  | #DIV/0! | 0
| € | Travel costs | 60669.27 | 15329.92 |  | 15329.92 | 25.27% | 45339.35
| € | Other costs and equipement | 6000 | 1294.13 |  | 1411.78 | 21.57% | 4705.87
| € | Indirect costs | 421447 | 146394.3 |  | 146394.3 | 34.74% | 275052.7
|  | Total costs | 1124825 | 388240.36 | 0 | 388240.36 | 34.52% | 753208.69
FHG |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
11 | in P/M | Total Person-month | 150 | 27.4 |  | 27.4 | 18.27% | 122.6
|  | Direct Costs | 997205 | 176123.58 |  |  | 17.66% | 821081.42
| € | Personnel costs | 923017 | 154598.04 |  |  | 16.75% | 768418.96
| € | Subcontract costs (except audit) |  | 0 |  |  | #DIV/0! | 0
| € | Subcontract (audit costs only) |  | 0 |  |  | #DIV/0! | 0
| € | Travel costs | 58478 | 21447.07 |  |  | 36.68% | 37030.93
| € | Other costs and equipement | 15710 | 78.47 |  |  | 0.4995% | 15631.53
| € | Indirect costs | 741460 | 129708.9 |  |  | 17.49% | 611751.1
|  | Total costs | 1738665 | 305832.48 | 0 | 0 | 17.59% | 1432832.52
BIOVISTA |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
12 | in P/M | Total Person-month | 73 | 26.4 | 0 | 26.4 | 36.16% | 46.6
|  | Direct Costs | 880168 | 111938.95 | 0 | 111938.95 | 12.72% | 768229.05
| € | Personnel costs | 574950 | 34897.12 |  | 34897.12 | 6.07% | 540052.88
| € | Subcontract costs (except audit) | 72000 | 0 |  | 0 | 0% | 72000
| € | Subcontract (audit costs only) | 0 | 0 |  | 0 | #DIV/0! | 0
| € | Travel costs | 53218 | 6922.79 |  | 6922.79 | 13.01% | 46295.21
| € | Other costs and equipement | 180000 | 70119.04 |  | 70119.04 | 38.96% | 109880.96
| € | Indirect costs | 60000 | 12955.14 |  | 12955.14 | 21.59% | 47044.86
|  | Total costs | 940168 | 124894.09 | 0 | 124894.09 | 13.28% | 815273.91
UoC |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
13 | in P/M | Total Person-month | 49 | 12 | 1.5 | 13.5 | 24.49% | 37
|  | Direct Costs | 218148 | 7306.5 | 6000 | 13306.5 | 3.349% | 210841.5
| € | Personnel costs | 205800 | 4664 |  | 4464 | 2.266% | 201136
| € | Subcontract costs (except audit) |  |  |  |  | #DIV/0! | 0
| € | Subcontract (audit costs only) |  |  |  |  | #DIV/0! | 0
| € | Travel costs | 12348 | 2642.5 |  | 2642 | 21.4% | 9705.5
| € | Other costs and equipement |  |  |  |  | #DIV/0! | 0
| € | Indirect costs | 43630 | 1461.3 |  | 1461.3 | 3.349% | 42168.7
|  | Total costs | 261778 | 8767.8 | 6000 | 14767.8 | 3.349% | 253010.2
LUH |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
14 | in P/M | Total Person-month | 31 | 18.4 | 5.92 | 24.32 | 59.35% | 12,60
|  | Direct Costs | 197357 | 60582.76 | 32135.73 | 92718.49 | 30.7% | 136774.24
| € | Personnel costs | 159267 | 50280.94 | 32135.73 | 50280.94 | 31.57% | 108986.06
| € | Subcontract costs (except audit) |  | 0 | 0 | 0 | #DIV/0! | 0
| € | Subcontract (audit costs only) |  | 0 | 0 | 0 | #DIV/0! | 0
| € | Travel costs | 35000 | 8829.04 | 0 | 8829.04 | 25.23% | 26170.96
| € | Other costs and equipement | 3090 | 1472.78 | 0 | 1472.78 | 47.66% | 1617.22
| € | Indirect costs | 39472 | 12116.55 | 0 | 4005.27 | 30.7% | 27355.45
|  | Total costs | 236829 | 72699.31 | 32135.73 | 96723.76 | 30.7% | 164129.69
PSNC |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
15 | in P/M | Total Person-month | 109 | 10.37 | 10 | 20.37 | 9.514% | 98.63
|  | Direct Costs | 496915 | 55154.04 | 66467 | 121621.04 | 11.1% | 441760.96
| € | Personnel costs | 429580.83 | 38123.81 |  | 38123.81 | 8.875% | 391457.02
| € | Subcontract costs (except audit) |  | 0 |  | 0 | #DIV/0! | 0
| € | Subcontract (audit costs only) |  | 0 |  | 0 | #DIV/0! | 0
| € | Travel costs | 50000 | 13152.73 |  | 13152.73 | 26.31% | 36847.27
| € | Other costs and equipement | 17334.17 | 3877.5 |  | 3877.5 | 22.37% | 13456.67
| € | Indirect costs | 99382 | 11030.8 |  | 11030.8 | 11.1% | 88351.2
|  | Total costs | 596297 | 66184.84 | 66467 | 132651.84 | 11.1% | 530112.16
CUSTODIX |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
16 | in P/M | Total Person-month | 63 | 31.55 |  | 31.55 | 50.08% | 31.45
|  | Direct Costs | 601020 | 204096.99 | 0 | 204096.99 | 33.96% | 396923.01
| € | Personnel costs | 553592 | 195999.85 |  |  | 35.41% | 357592.15
| € | Subcontract costs (except audit) |  | 0 |  |  | #DIV/0! | 0
| € | Subcontract (audit costs only) |  |  |  |  | #DIV/0! | 0
| € | Travel costs | 47428 | 6940.74 |  |  | 14.63% | 40487.26
| € | Other costs and equipement | 0 | 1156.4 |  |  | #DIV/0! | -1156.4
| € | Indirect costs | 240408 | 78399.94 |  |  | 32.61% | 162008.06
|  | Total costs | 841428 | 282496.93 | 0 | 204096.99 | 33.57% | 558931.07
HEALTHGRID |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
17 | in P/M | Total Person-month | 45 | 19.8 | 0.5 | 20.3 | 44% | 25.2
|  | Direct Costs | 267120 | 61038 | 2000 | 63038 | 22.85% | 206082
| € | Personnel costs | 207120 | 47029 |  |  | 22.71% | 160091
| € | Subcontract costs (except audit) | 0 | 0 |  |  | 0% | 0
| € | Subcontract (audit costs only) | 0 | 0 |  |  | 0% | 0
| € | Travel costs | 40000 | 9787 |  |  | 24.47% | 30213
| € | Other costs and equipement | 20000 | 4222 |  |  | 21.11% | 15778
| € | Indirect costs | 53424 | 12207.6 |  |  | 22.85% | 41216.4
|  | Total costs | 320544 | 73245.6 | 2000 | 63038 | 22.85% | 247298.4
ICCS |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
18 | in P/M | Total Person-month | 58 | 16.9 | 4.5 | 21.4 | 29.14% | 41.1
|  | Direct Costs | 384127 | 82418.97 | 12420 | 94838.97 | 21.46% | 301708.03
| € | Personnel costs | 328127 | 73816.2 | 12420 |  | 22.5% | 254310.8
| € | Subcontract costs (except audit) | 0 | 0 | 0 |  | #DIV/0! | 0
| € | Subcontract (audit costs only) | 0 | 0 | 0 |  | #DIV/0! | 0
| € | Travel costs | 28000 | 8304.67 | 0 |  | 29.66% | 19695.33
| € | Other costs and equipement | 28000 | 298.1 | 0 |  | 1.065% | 27701.9
| € | Indirect costs | 76825 | 16483.794 | 0 |  | 21.46% | 60341.206
|  | Total costs | 460952 | 98902.764 | 12420 | 94838.97 | 21.46% | 362049.236
USSAR |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
19 | in P/M | Total Person-month | 93 | 20.19 | 11.86 | 32.05 | 21.71% | 72.81
|  | Direct Costs | 567545 | 94168.85 | 60000 | 154168.85 | 16.59% | 473376.15
| € | Personnel costs | 488250 | 81302.83 | 60000 | 141302.83 | 16.65% | 406947.17
| € | Subcontract costs (except audit) | 0 | 0 | 0 | 0 | #DIV/0! | 0
| € | Subcontract (audit costs only) | 0 | 0 | 0 | 0 | #DIV/0! | 0
| € | Travel costs | 29295 | 12103.78 | 0 | 12103.78 | 41.32% | 17191.22
| € | Other costs and equipement | 50000 | 762.24 | 0 | 762.24 | 1.524% | 49237.76
| € | Indirect costs | 113509 | 18833.77 | 12000 | 30833.77 | 16.59% | 94675.23
|  | Total costs | 681054 | 113002.62 | 72000 | 185002.62 | 16.59% | 568051.38
SIVECO |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
20 | in P/M | Total Person-month | 63 | 14 | 0 | 14 | 22.22% | 49
|  | Direct Costs | 265050 | 49539 | 0 | 49539 | 18.69% | 215511
| € | Personnel costs | 238045 | 43120 | 0 | 43120 | 18.11% | 194925
| € | Subcontract costs (except audit) | 0 | 0 | 0 | 0 | #DIV/0! | 0
| € | Subcontract (audit costs only) | 0 | 0 | 0 | 0 | #DIV/0! | 0
| € | Travel costs | 27005 | 6419 | 0 | 6419 | 23.77% | 20586
| € | Other costs and equipement | 0 | 0 | 0 | 0 | #DIV/0! | 0
| € | Indirect costs | 212040 | 39239.2 | 0 | 39239.2 | 18.51% | 172800.8
|  | Total costs | 477090 | 88778.2 | 0 | 88778.2 | 18.61% | 388311.8
FUNDP |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
21 | in P/M | Total Person-month | 49 | 12 | 1 | 13 | 24.49% | 37
|  | Direct Costs | 233730 | 58416.75 |  | 58416.75 | 24.99% | 175313.25
| € | Personnel costs | 202840 | 49276.62 | 8600.36 | 57876.98 | 24.29% | 153563.38
| € | Subcontract costs (except audit) |  |  |  | 0 | #DIV/0! | 0
| € | Subcontract (audit costs only) |  |  |  | 0 | #DIV/0! | 0
| € | Travel costs | 26390 | 8507.5 |  | 8507.5 | 32.24% | 17882.5
| € | Other costs and equipement | 4500 | 632.63 |  | 632.63 | 14.06% | 3867.37
| € | Indirect costs | 46746 | 11683.35 |  | 11683.35 | 24.99% | 35062.65
|  | Total costs | 280476 | 70100.1 | 8600.36 | 70100.1 | 24.99% | 210375.9
Participant UH |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
22 | in P/M | Total Person-month | 36 | 10.75 | 3 | 14 | 29.86% | 25.25
|  | Direct Costs | 203011 | 53690.26 | 18521.37 | 72211.63 | 26.45% | 149320.74
| € | Personnel costs | 191521 | 48693.81 |  |  | 25.42% | 142827.19
| € | Subcontract costs (except audit) | 0 | 0 |  |  | #DIV/0! | 0
| € | Subcontract (audit costs only) | 0 | 0 |  |  | #DIV/0! | 0
| € | Travel costs | 11490 | 4996.45 |  |  | 43.49% | 6493.55
| € | Other costs and equipement | 0 | 0 |  |  | #DIV/0! | 0
| € | Indirect costs | 40602 | 10738.052 |  | 10738.052 | 26.45% | 29863.948
|  | Total costs | 243613 | 64428.312 | 18521.37 | 82949.682 | 26.45% | 179184.688
UOXF |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
23 | in P/M | Total Person-month | 56 | 3.37 | 7.43 | 10.8 | 6.018% | 52.63
|  | Direct Costs | 382416 | 15411.72 | 48828.42 | 64240.14 | 4.03% | 367004.28
| € | Personnel costs | 321601 | 15411.72 | 48828.42 | 64240.14 | 4.792% | 306189.28
| € | Subcontract costs (except audit) | 0 | 0 |  | 0 | #DIV/0! | 0
| € | Subcontract (audit costs only) | 0 | 0 |  | 0 | #DIV/0! | 0
| € | Travel costs | 10815 | 0 |  | 0 | 0% | 10815
| € | Other costs and equipement | 50000 | 0 |  | 0 | 0% | 50000
| € | Indirect costs | 76483 | 3082.34 | 9765.68 | 12848.02 | 4.03% | 73400.66
|  | Total costs | 458899 | 18494.06 | 58594.1 | 77088.16 | 4.03% | 440404.94
UHOK No funding |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
24 (CPF 25) | in P/M | Total Person-month | 29 |  | 4.5 | 4.5 | 0% | 29
|  | Direct Costs | 206570 | 0 | 52623 | 52623 | 0% | 206570
| € | Personnel costs | 206570 |  | 23963 | 23963 | 0% | 206570
| € | Subcontract costs (except audit) |  |  |  | 0 | #DIV/0! | 0
| € | Subcontract (audit costs only) |  |  |  | 0 | #DIV/0! | 0
| € | Travel costs |  |  | 28660 | 28660 | #DIV/0! | 0
| € | Other costs and equipement |  |  |  | 0 | #DIV/0! | 0
| € | Indirect costs | 41314 |  | 10524.6 | 10524.6 | 0% | 41314
|  | Total costs | 247884 | 0 | 63147.6 | 63147.6 | 0% | 247884
IEO |  | Type of Expenditure (as defined by participants) | Budget for the whole duration of the project | Period 1 01/02/2006 TO 31/01/2007 |  |  | % Spent versus actual costs | Remaining Budget (EUR) versus actual costs
|  | AMOUNT IN EURO |  | Actual costs | AC Global estimate (Permanent staff only) | TOTAL
25 (CPF 26) | in P/M | Total Person-month | 35 | 0 | 7.5 | 7.5 | 0% | 35
|  | Direct Costs | 207507 | 807 | 52000 | 52807 | 0.3889% | 206700
| € | Personnel costs | 195057 | 0 | 52000 | 0 | 0% | 195057
| € | Subcontract costs (except audit) | 0 | 0 | 0 | 0 |  | 0
| € | Subcontract (audit costs only) | 0 | 0 | 0 | 0 |  | 0
| € | Travel costs | 12450 | 807 | 0 | 0 | 6.482% | 11643
| € | Other costs and equipement | 0 | 0 | 0 | 0 |  | 0
| € | Indirect costs | 41501 | 161.4 | 10400 | 10561.4 | 0.3889% | 41339.6
|  | Total costs | 249008 | 968.4 | 62400 | 63368.4 | 0.3889% | 248039.6